## Sheet1
WBS Code | Task/Module | Description | Owner | Start-Date | End-Date | Effort-taken | Status
1 | Periyar Stores Project | Complete Web application | Nitesh | December 23 rd | January 5th | 80 Hours | Ongoing
2 | User Management | Signup,Login |  | December 26th | December 29 th | 24 hours | Done
3 | Forms validation used Template Driven Forms | Signup,Login |  | December 26th | December 29th | 24 hours | Done
4 | Product Display Page | Entire Products available in db will be shown |  | December 30th | January 2nd | 24 hours | Done
5 | Product Description Page | Detailed information about particular product |  | December 30 th | January 2nd | 24 hours | Done
6 | Cart Page | Products added by user to buy in future |  | January 2nd | January 5th | 32 hours | Ongoing
7 | Buy now | From cart page user select the product to buy |  | January 2nd | January 5th | 32 hours | Ongoing
8 | Form to be filled | Need to give personal details about user to deliver th product. Only cash on delivery is allowed in our project.As per client request payment section will be added in next phase |  | January 2nd | January 5th | 32 hours | Ongoing